## Deployment Activities
S.No. | Activity Description | Server | Owner (Name) | Owner (Team Name) | Status (Task progress) | Environment (PROD or DR) | Is DR replication applicable? (If no, justfiy) | Downtime (Duration) | Timelines (Duration) | Start Date | Start Time | End Date | End Time | Justifcation on the selected schedule (if it is during business hours) | Additonal Remarks
1 | Snapshot of PRD - NMS Server | NMS | Guru | Bank Muscat | Backup | PROD | Single Environment | No downtime
2 | Snapshot of PRD - NSS Server | NSS | Guru | Bank Muscat | Backup | PROD | Single Environment | No downtime
3 | Nuance Backup Files | NMS/NSS | Guru,Ranjith,Manoj | Bank Muscat,Servion | Backup | PROD | Single Environment | No downtime
4 | Nuance Configuration Files NMS(tomcat server.xml, mserver-configure.log, mserver_cfg.properties) and NSS Server(config folder, diagnosticLogs) | NMS/NSS | Guru,Ranjith,Manoj | Bank Muscat,Servion | Backup | PROD | Single Environment | No downtime
5 | NMS Tomcat / Grammer File Tomcat | NMS/NSS | Guru,Ranjith,Manoj | Bank Muscat,Servion | Backup | PROD | Single Environment | No downtime
6 | Java Zulu11 OpenJdk | NMS/NSS | Guru,Ranjith,Manoj | Bank Muscat,Servion | Backup | PROD | Single Environment | No downtime
7 | My Tomcat Home 9.0.x - NMS (zip file) | NMS | Guru,Ranjith,Manoj | Bank Muscat,Servion | Software Installation | PROD | Single Environment | No downtime
8 | Apache Tomcat 9.0.x - Grammer File (exe file) | NSS | Guru,Ranjith,Manoj | Bank Muscat,Servion | Software Installation | PROD | Single Environment | No downtime
9 | Java Zulu11 OpenJdk (msi file) | NMS/NSS | Guru,Ranjith,Manoj | Bank Muscat,Servion | Software Installation | PROD | Single Environment | No downtime
10 | NMS Tomcat Upgrade - Refer - NMS Tomcat Upgrade tab | NMS | Guru,Ranjith,Manoj | Bank Muscat,Servion | NMS Tomcat Upgrade | PROD | Single Environment | 0.5
11 | NMS/NSS Java Zulu11 OpenJdk Upgrade - Refer - NMS_NSS Java Upgrade tab | NMS/NSS | Guru,Ranjith,Manoj | Bank Muscat,Servion | Java Upgrade | PROD | Single Environment | 0.5
12 | Nuance Grammer Tomcat Upgrade (server.xml, .jks file, BM_DATA folder) | NSS | Guru,Ranjith,Manoj | Bank Muscat,Servion | Grammar Tomcat Upgrade | PROD | Single Environment | 0.5

## Roll_Back_Activities
S.No. | Activity Description (RollBack) | Rollback Triggers | Rollback Sub-Triggers | Has the rollback been tested? | Who tested the rollback? (Team Name) | Rollback Duration | Additonal Remarks
1 | Remove the PROD snapshot to revert to the older version – NMS Server
2 | Remove the PROD snapshot to revert to the older version – NSS Server
| Rollback Triggers | System_Crashes | Performance_Degradation_or_System_Health | Functional_Failures | User-Complaince | Monitoring Alerts | Other
| System_Crashes | Service unavailability or downtime | Increased response times | New features don’t work as intended
| Performance_Degradation_or_System_Health | Failures in dependent systems | System resource overuse (CPU, memory usage…etc.) | Login Issue
| Functional_Failures | Others | Others | Business-critical workflows are disrupted
| User-Complaince |  |  | Core functionality is broken (e.g. Payment Processing)
Monitoring-Alerts
Other

## Monitoring Plan
S.No. | Activity Description | Owner (Name) | Owner (Team Name) | Status (Task progress) | Start Date | Start Time | End Date | End Time | Additonal Remarks
1 | Log in to the NMS portal and check all services are up and running | Guru,Ranjith,Manoj | Bank Muscat,Servion | NMS Portal Services
2 | Open the windows services and check all nuance services are up and running | Guru,Ranjith,Manoj | Bank Muscat,Servion | Nuance Windows Services
3 | Test the POM application | Guru | Bank Muscat | POM application
4 | Monitor application performance | Guru | Bank Muscat | Monitor application

## NMS Tomcat Upgrade
S.No | Steps | Note
1 | Log in to the Management Station | https://docs.nuance.com/speech-suite/ms/upgrading-tomcat.html
2 | Stop all the Management Station services in NMS Portal
3 | Open windows services stop below services: Order to Stop Services in NMS : Nuance Management Station Nuance Management Station Data Collection Nuance Management Station state Analyser Nuance Watcher Deamon Nuance License Service
4 | Locate the Tomcat update script: On Windows: C:\Program Files\Nuance\Management Station\mstation\mserver\webapps\mserver\scripts\update_tomcat.bat
5 | Execute the Tomcat update script: On Windows: Open a command prompt window with the Run as Administrator option. Run this command at the prompt, specifying the paths to your old and new Tomcat installations: > update_tomcat.bat old_tomcat_location new_tomcat_location > update_tomcat.bat C:\Program Files\Apache Software Foundation\Tomcat 10.1.41 C:\Program Files\Apache Software Foundation\Tomcat 10.1.57 > update_tomcat.bat C:\PROGRA~1\APACHE~1\TOMCAT~2.41 C:\PROGRA~1\APACHE~1\TOMCAT~2.57 | Note: If a path contains spaces, you must use 8.3 naming convention. You cannot wrap the path in quotes. An error message displays if the script detects an unsupported Tomcat version. You need to install a supported version of Tomcat and then repeat this procedure. dir /x "C:\Program Files\Apache Software Foundation" Open mserver-configure.log and check the tomcat_home path MY_TOMCAT_HOME=C:\PROGRA~1\APACHE~1\TOMCAT~2.41
6 | Configure https cert in server.xml in nms tomcat | Not Required(Skip this step)
7 | Reboot NMS System
8 | Start the Management Station services to complete the update: On Windows, use the Services dialog. Order to Start Services in NMS : Nuance License Service Nuance Management Station Nuance Management Station Data Collection Nuance Management Station state Analyser Nuance Watcher Daemon
9 | Start all the Management Station services in NMS Portal

## NMS_NSS Java Upgrade
S.No | Steps | Note
1 | Log in to the Management Station | https://docs.nuance.com/speech-suite/core-install/si-proc-upg-java.html
2 | Stop all the Management Station services in NMS Portal
3 | Open windows services stop below services: Order to Stop Services in NMS : Nuance Management Station Nuance Management Station Data Collection Nuance Management Station state Analyser Nuance Watcher Deamon Nuance License Service
4 | Take backup of existing folder zulu11 and choose same path while running .msi file
4 | Configure JAVA_HOME inside Environmental Variables both NMS and NSS | C:\Program Files\Zulu\zulu-11
5 | If we are using Dragon voice services(Nuance Resource Manager, Krypton, NLE, and NTpE) Import the certificates for Speech Suite services to the new keystore. | There is a separate way to update JAVA ( certificate import needs to be done)
6 | Confirm that the Java path is updated correctly using cmd | >echo %JAVA_HOME% >java -version
7 | Reboot NMS/NSS System
8 | Start the Management Station services to complete the update: On Windows, use the Services dialog. Order to Start Services in NMS : Nuance License Service Nuance Management Station Nuance Management Station Data Collection Nuance Management Station state Analyser Nuance Watcher Daemon
9 | Start all the Management Station services in NMS Portal